## Known Issues
Please make sure to set the proper IDs into the filename!
This is the only sheet that needs to be edited! Delete the examples below and fill it with your own data.
| # | Type | Sub Type | Description | Severity | Reproducibility | Reproduce steps | Reason | Reason notes
| 1 | Feature | "Smart charging algorithm" | Didn't implement a smart algorithm for charging, such that stays at docking in an efficent way to maximize cleaining and minimize steps. Instad the robot staying in docking until it fully charged (If needed- if max battery will benefit the robot- else finish). the robot IS finish if there is no point in charging (not enogh max steps for charge and get to nearest rewuired tile...) | Medium | Sometimes | House that the dirt in not rewuire staying in docking until fully charged. | Lack of time | I created a smart algorithm with "smart charging" but did not have enogh time to check it on all inputs. If you are intresting I added it to a folder named KnownIsuues. [Explain: calculateChargingTime is being called when robot is in docking, it explore in a BFS way the tiles, while randoming dirt for unkown tiles. it saves the path, steps to charge of the path that gives us the maximum dirt, all of this under the limitation of maxSteps and maxBatterySteps. in getStepFromMapping, if onDeterminedWayFromCharging is true, we keep charging as the amount of steps for charging that was determined on calculateChargingTime and when finishing, making the path that also was determined there. other seggestions based on this implementation is change the amount of dirt of the unkwon tiles (maybe to 0 or 1...). TO SUM UP: this algorithm searches using BFS method after the path with maximum dirt that id we will go on it we will have enogh steps in battery and max steps]
| 2 | Feature | Algorithms might be slow | In Algorithm A: In worst case the in getStepFromMapping (houseMappingGraph.cpp) there can be at most 3 runs of BFS (that might not occure in next steps because they build a path for next steps). | Medium | Sometimes | Tiles with dirt and unkwon dirt in equal distance from current location. Robot dont have enogh steps to clean closest tile with dirt- will need to calculate distance between docking station and tile with unkwon dirt to check if this option is possibole with current steps. | Lack of time | I didn’t want to change the code 1 day before submission, so prefered keep it this way. Also, my algorithm not calculating BFS In every step, there are iteration where the step is getting in O(1) time, so it offsetting.
| 3 | Code | coding convention for file names | names of cpp and h file is not unit (some with upper cases and some with _) | Low | Always |  | I did not know if Im allowed to change the names of the files you gave to us in the skeleton, so I kept mine as it is (my files have the same naming conventions). | Tried to fix that but it caused the program to crash...C11B7:J9
| 4 | Code | long functions | In Task.cpp, the function Task::run is pretty long because of the body of jthread | Low | Always |  | Lack of time | Did not had the time to put jthread body in different function (it is possibole and better..)

## Issue Types and Sub-Types
Types | Sub-Types
Feature | Feature Missing
Feature Partially Missing
Feature developed in a different way
Bug | Program crash
Program misbehave
Coding | Missing a required Class
Having a redundant Class (see example below)
Code duplication
Function is too long
Class is doing a job of another class
Spread logic (logic of a certain operation is spread into too many places in code)
Code is too complex (could be written in a more elegant way)
Use of hard coded numbers instead of enums / constants (no need to document per case)
Bad names for functions / classes / variables (no need to document per case)
Other

## Issue Severity
Issue Severity
High
Medium
Low

## Issue Reproducibility
Issue Reproducibility
Always
Sometimes
Not relevant

## Issue Reason
Issue Reason
Lack of time
Lack of knowledge